## project (2)
Project Schedule
[7 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual | % Complete
[8 empty] | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ASSIGNED TO | ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
| Design Document | 1 | 1 | 1 | 1 | 100%
| Pick Game | 2 | 1 | 2 | 1 | 100%
| Pick Engine | 2 | 1 | 2 | 1 | 100%
| Pick Content Tools | 2 | 1 | 2 | 1 | 100%
| Project Scope Documention | 3 | 1 |  |  | 0%
| Content Identification | 4 | 1 |  |  | 0%
| Project Blog Creation | 5 | 1 |  |  | 0%
| Project GitHub Creation | 5 | 1 |  |  | 0%
| Project Trello Creation | 5 | 1 |  |  | 0%
| Player Mechanics Document | 6 | 2 |  |  | 0%
| NPC Mechanics Document | 6 | 2 |  |  | 0%
| Required Content Document | 8 | 1 |  |  | 0%
| GitHub Setup | 9 | 1 |  |  | 0%
| Player Character Prototype | 9 | 7 |  |  | 0%
| NPC Characters Prototype | 16 | 7 |  |  | 0%
| Collectibles/Items | 24 | 4 |  |  | 0%
| Game Menus and HUD | 28 | 2 |  |  | 0%
| HUD Content | 30 | 2 |  |  | 0%
| Levels Mesh Out | 32 | 7 |  |  | 0%
| Levels Lighting | 39 | 2 |  |  | 0%
| Menus Content | 41 | 4 |  |  | 0%
| Player Character Final | 45 | 14 |  |  | 0%
| NPC Characters Final | 59 | 4 |  |  | 0%
| Game Loading and Saving | 64 | 1 |  |  | 0%
| Game Audio Sourcing | 65 | 1 |  |  | 0%
| Audio Importing | 66 | 1 |  |  | 0%
| Project Packaging | 80 | 5 |  |  | 0%
| Final Presentation | 85 | 5 |  |  | 0%